## Sheet1
Module | Task List | Sub Task | Start Date | End Date | Estimated Efforts | Actual Efforts | Assignee Name | Status
Security |  |  | 2022-05-10 | 2022-05-13 |  |  | Ravi | done
Configuration
|  | User Authentication |  |  |  | 16
|  | User Autherization |  |  |  | 16
| Login Page |  |  |  |  | 8 | Aparna
| Login Controller |  |  |  |  | 8
Home Page |  |  | 2022-05-11 | 2022-05-12 |  |  | Aparna | done
| Navbar |  |  |  |  | 8
| Home |  |  |  |  | 8
| Footer |  |  |  |  | 8
Asset |  |  | 2022-05-12 | 2022-05-14 |  |  |  | in progress
| Asset Page |  |  |  |  | 8 | Aparna
| Asset[CRUD] |  |  |  |  | 16 | Aparna,Ravi
| Add MasterData(Asset Type) | [6 empty] | not done
Accessory | [7 empty] | in progress
| Accessory Page |  | 2022-05-13 | 2022-05-14 |  | 8 | Aparna
| Accessory(CRUD) |  |  |  |  | 16 | Aparna,Ravi
| Add Master Data(Accessory Type) | [6 empty] | not done
Asset Assignment |  |  | 2022-05-15 | 2022-05-17 |  |  |  | in progress
| Asset Assignment Page |  |  |  |  | 8 | Aparna
| Asset Assignment [CRUD] |  |  |  |  | 16 | Aparna,Ravi
| Add Asset | [6 empty] | not done
| Add Master Data(Employee) | [6 empty] | not done
Accessory Issue |  |  | 2022-05-17 | 2022-05-17 |  |  |  | in progress
| Accessory Issue Page |  |  |  |  | 8 | Aparna
| Accessory Issue[CRUD] |  |  |  |  | 16 | Aparna,Ravi
| Add Accessory | [6 empty] | not done
| Add Master Data ( Employee) | [6 empty] | not done
Master Data
| Asset type |  | 2022-05-13 | 2022-05-14 |  |  |  | done
|  | view page |  |  |  | 8 | Aparna
|  | save & update page |  |  |  | 8 | Aparna
|  | Asset type [CRUD] |  |  |  | 16 | Ravi,Aprana
| Accessory Type |  | 2022-05-14 | 2022-05-15 |  |  |  | done
|  | view page |  |  |  | 8 | Ravi
|  | save & update page |  |  |  | 8 | Ravi
|  | Accessory type [CRUD] |  |  |  | 16 | Ravi
| Employee |  | 2022-05-15 | 2022-05-15 |  |  |  | done
|  | view page |  |  |  | 8 | Aparna
|  | save & update page |  |  |  | 8 | Aparna
|  | Employee [CRUD] |  |  |  | 16 | Aparna,Ravi

## todo
Task List | Sub Task | 2022-05-18 | Status
mapping |  |  | done
asset
accessory
asset assignment
controller |  |  | done
asset
asset assignment
asset type
accessory
accessory type
accessory issues
employee